## Sprint WBS (Tasks)
DebateSpeak AI — DevOps & QA / Fact-Checking Lead WBS
Owner: Nguyễn Đình Thiên Lộc (Student ID: 24125093) ¦ Role: R5 ¦ 5 Sprints (PA1–PA5)
Task ID | Sprint / PA | Category | Task Description & Objective | Deliverable / File Artifact | Reviewer | Story Points | Priority | Status
T1.1 | Sprint 1 (PA1) | DevOps / CI | Repository setup, monorepo layout, code style linters (Ruff, ESLint), GitHub Actions CI | .github/workflows/ci.yml | R2 (Tài) | 3 | CRITICAL | Done
T1.2 | Sprint 1 (PA1) | DevOps / Infra | Docker Compose setup for local dev (PostgreSQL 16, Redis 7, LiveKit dev) & clean .env.example | docker-compose.yml, .env.example | R2 (Tài) | 3 | CRITICAL | Done
T1.6 | Sprint 1 (PA1) | Management | Setup Dev Tools, Scrum Process & Incremental Slices specification | docs/management/DEV_TOOLS_AND_PROCESS.md | R2 (Tài) | 3 | MAJOR | Done
T1.8 | Sprint 1 (PA1) | QA / Testing | Draft comprehensive QA & Testing Plan (Unit, Integration, Audio chaos, Golden sets) | docs/testing/TESTING_PLAN.md | R3 (Khoa) | 5 | CRITICAL | Done
T1.9 | Sprint 1 (PA1) | Academic / LaTeX | Configure latexmk academic report compilation pipeline & compile submission PDF | report/report.tex, report/build/report.pdf | R1 (Triết) | 2 | MAJOR | Done
T2.1 | Sprint 2 (PA2) | Management | Author Project Plan: Goals, deliverables, risks, 5-sprint schedule, build plan | docs/pa2/PROJECT_PLAN.md | R1 (Triết) | 5 | CRITICAL | In Progress
T2.3 | Sprint 2 (PA2) | SDD / Spec Kit | Spec Kit Initialization in /src: constitution.md and initial spec artifacts | src/constitution.md, .specify/ | R4 (Tuấn) | 3 | CRITICAL | Done
T2.R | Sprint 2 (PA2) | QA / Review | Verify Backend Build 1: PostgreSQL migrations, Argon2id auth, JWT rotation, and room lobby endpoints | api/tests/unit/test_auth.py | R2 (Tài) | 2 | MAJOR | Planned
T3.1 | Sprint 3 (PA3) | Management | Revised Project Plan & Vision Document with Changes.md (incorporating TA feedback) | docs/pa3/Changes.md | R1 (Triết) | 3 | MAJOR | Planned
T3.R | Sprint 3 (PA3) | QA / Testing | E2E testing of Functional Group 03 (Room & Live Session Management) with mock clients | tests/e2e/test_rooms_lobby.py | R1 (Triết) | 3 | CRITICAL | Planned
T4.4 | Sprint 4 (PA4) | DevOps / Infra | Author Deployment Diagram & setup Caddy TLS reverse proxy on staging VM (mic permission HTTPS) | docs/pa4/DEPLOYMENT_DIAGRAM.md, Caddyfile | R2 (Tài) | 5 | CRITICAL | Planned
T4.7 | Sprint 4 (PA4) | Management | Sprint 4 AI Usage Report & Weekly Report (Scrum metrics, token consumption) | docs/pa4/WEEKLY_REPORT.md | R1 (Triết) | 2 | MAJOR | Planned
T4.R | Sprint 4 (PA4) | QA / Audio | Validate audio streaming pipeline under latency & packet loss chaos tests (Playwright fake media) | tests/e2e/test_audio_stream.py | R3 (Khoa) | 3 | CRITICAL | Planned
T5.1 | Sprint 5 (PA5) | QA / Testing | Execute Test Plan & Refine Test Cases: Negative edge cases, state machine violations, grounding guard | docs/pa5/TEST_EXECUTION_REPORT.md | R2 (Tài) | 5 | CRITICAL | Planned
T5.2 | Sprint 5 (PA5) | QA / Defects | Document pass/fail matrix, triage bug reports, and verify zero open P0/P1 defects | docs/pa5/DEFECT_MATRIX.md | R4 (Tuấn) | 3 | CRITICAL | Planned
T5.3 | Sprint 5 (PA5) | Fact-Checking | Fact-Checking Engine Hardening: Claim detection threshold, search retrieval sanitization, and Skeptic consensus | workers/analysis/factcheck.py | R2 (Tài) | 5 | CRITICAL | Planned
T5.6 | Sprint 5 (PA5) | Management | Author Final Reflective Report: SDLC critique, tooling evaluation, individual workload distribution | docs/pa5/REFLECTIVE_REPORT.md | All Leads | 5 | CRITICAL | Planned
T5.7 | Sprint 5 (PA5) | DevOps / Release | Final Codebase Freeze, tag release v5.0-final, and package submission ZIP archive | PA5-Group01.zip | All Leads | 2 | CRITICAL | Planned

## Immediate Action Plan
Immediate Tactical Action Plan — Next 7 Days
Priority sequence to unblock team members (Tài, Triết, Khoa, Tuấn)
Step | Action Item | Target Directory / File | Why It Matters | Unblocks Whom? | Est. Time | Status
Step 1 | Local Docker Compose Infrastructure Setup | docker-compose.yml, .env.example | Run PostgreSQL 16, Redis 7, LiveKit locally with 1 command | Everyone | Completed | Done
Step 2 | Update README.md with Quick Start & Health Checks | README.md | Teammates and evaluators can boot and verify the system in 2 mins | Everyone / Graders | Completed | Done
Step 3 | Monorepo Directory Layout Scaffolding | api/, web/, workers/, tests/, scripts/ | Establishes clean architecture layout per TESTING_PLAN.md | Tài (R2), Triết (R1) | Completed | Done
Step 4 | Backend & Frontend Linter Configurations | api/pyproject.toml, web/eslint.config.js | Enforce Ruff, Mypy, ESLint so code committed is clean and formatted | All coders | Completed | Done
Step 5 | GitHub Actions CI Pipeline (.github/workflows/ci.yml) | .github/workflows/ci.yml | Automates linting, security audits, tests, and latexmk build | All PRs | Completed | Done
Step 6 | Draft PA2 Project Plan Document (T2.1) | docs/pa2/PROJECT_PLAN.md | Formal PA2 deliverable: Goals, risks, 5-sprint schedule, build roadmap | Course submission | 2 hours | In Progress

## QA & Testing Matrix
QA Testing Strategy & Quality Gates (NFR-15 Enforcement)
Automated gates required for merging into develop and releasing to main
Test Level | Target Component | Testing Framework | Success Criterion | CI Automation | Frequency
Unit Testing | Backend Auth, Room State Machine, Pydantic schemas | pytest, pytest-asyncio | >= 70% line coverage on core business logic | Yes (GitHub Actions) | Every PR
Integration Testing | FastAPI + PostgreSQL + Redis (Token minting, session state) | pytest, respx, testcontainers / service containers | 100% pass on state transition fixtures | Yes (GitHub Actions) | Every PR
Frontend Unit & Component | React components, audio volume bars, transcript viewer | Vitest, React Testing Library | Zero rendering regressions, 100% pass | Yes (GitHub Actions) | Every PR
E2E WebRTC Smoke Test | Two mock users entering room, subscribing to audio | Playwright with fake media flags | Room transitions from LOBBY -> LIVE -> COMPLETED | Yes (Scheduled/PR) | Nightly & PR
Security & Vulnerability | Python packages (pip-audit), npm dependencies, secrets scan | pip-audit, npm audit, Gitleaks | Zero critical/high vulnerabilities; 0 secret leaks | Yes (GitHub Actions) | Every commit
Golden Set LLM Eval | Language Coach, Argument Coach, Consensus Judge | Golden evaluation benchmark scripts | 0 hallucinated quotes; 100% quote grounding | Semi-automated | Weekly sprint end
Academic LaTeX Build | Course PDF submission report (report/report.tex) | latexmk -pdf | 0 compilation fatal errors, clean PDF output | Yes (GitHub Actions) | Every push to docs/report

## Cost & Budget Model
DebateSpeak AI — Operational Cost Model (Per 10-Minute Debate)
Standardized calculation enforcing NFR-14 (Cost Control < $0.25 / debate budget)
Cost Category | Service / Provider | Usage Metric (10-Min Debate) | Unit Pricing ($) | Estimated Cost ($) | Optimization Guardrail | Risk / Buffer
WebRTC Audio Routing | LiveKit Cloud Free Tier | 20 participant-minutes (2 debaters x 10 min) | 0 | 0 | Free tier covers 10,000 mins/mo (~500 debates) | Zero cost within quota
Speech-to-Text (STT) | Deepgram Nova-2 Streaming | 20 audio-minutes (2 independent speaker tracks) | 0.0043 | 0.086 | Fallback: self-hosted faster-whisper ($0.00) | Medium (highest variable cost)
LLM: Language Coach | Gemini 1.5 Flash / GPT-4o-mini | ~4,000 input tokens, 800 output tokens | 0.00025 | 0.0015 | Chunk by speaker turn (~300 words), not whole transcript | Low (ultra-cheap flash models)
LLM: Argument Coach | Gemini 1.5 Flash / GPT-4o-mini | ~4,000 input tokens, 1,000 output tokens | 0.00025 | 0.0016 | Only process substantive argument turns | Low
LLM: Claim Detection | Gemini 1.5 Flash / GPT-4o-mini | ~3,000 input tokens, 500 output tokens | 0.00025 | 0.001 | Sentence-by-sentence check-worthiness filter | Low
LLM: Skeptic & Judge | Gemini 1.5 Flash / GPT-4o-mini | ~4,000 input tokens, 1,500 output tokens | 0.00025 | 0.002 | Pass summarized coach outputs, not raw audio text | Low
Search / Fact-Checking | Serper API / Tavily | Top 8 check-worthy claims x 2 queries = 16 queries | 0.001 | 0.016 | Strict cap at Top-N claims (N=8) with score >= 0.6 | Medium (queries blow up if not capped)
Fixed Hosting (Monthly) | Hetzner Cloud VPS (CPX21) | 1 month staging VM (3 vCPU, 4GB RAM, Caddy HTTPS) | 10 | 0.02 | Amortized across ~500 debate sessions/mo | Fixed ~$10/month
TOTAL ESTIMATED COST PER 10-MINUTE DEBATE |  |  |  | 0 | CONFIRMED WELL BELOW $0.25 BUDGET LIMIT (NFR-14)